## RCA Catalog
RCA ID | Incident Title | Category | Severity | Date Identified | Affected System | Impact Description | Root Cause Summary | RCA Methodology | Status | Owner | Days to Resolve
RCA-001 | EHR System Outage During Peak Hours | Application | Critical | 2025-09-12 | Epic EHR | Complete EHR downtime for 3 hours affecting 450+ clinicians; patient care delays in ED and ICU | Database connection pool exhaustion due to unoptimized query from recent patch deployment | 5 Whys + Fishbone | Closed | Dr. S. Patel | 14
RCA-002 | HL7 Interface Engine Message Backlog | Integration | High | 2025-09-28 | Rhapsody Interface Engine | 12,000+ HL7 messages queued; lab results delayed 4+ hours across 3 hospitals | Memory leak in HL7 parser module after upgrade to v6.2; garbage collection unable to reclaim heap | 5 Whys + Fishbone | Closed | J. Williams | 10
RCA-003 | PACS Image Retrieval Failure | Infrastructure | Critical | 2025-10-05 | GE Centricity PACS | Radiology unable to retrieve prior imaging studies; 85 diagnostic delays reported | SAN storage controller firmware bug caused intermittent I/O errors on PACS archive LUNs | 5 Whys + Fishbone | Closed | M. Chen | 21
RCA-004 | Patient Portal Authentication Bypass Vulnerability | Security | Critical | 2025-10-18 | MyChart Patient Portal | Security scan revealed authentication bypass allowing unauthorized PHI access; zero confirmed exploits | Improper session token validation in OAuth2 callback handler; tokens not expiring after password change | 5 Whys + Fishbone | Closed | R. Johnson | 7
RCA-005 | Medication Dispensing Cabinet Network Failure | Network | High | 2025-11-02 | Omnicell ADC Cabinets | 32 Pyxis/Omnicell cabinets offline across 2 campuses; manual medication dispensing for 6 hours | VLAN misconfiguration during network switch replacement; DHCP scope conflict on biomedical device subnet | 5 Whys + Fishbone | Closed | A. Rodriguez | 5
RCA-006 | Clinical Decision Support Alert Fatigue | Application | Medium | 2025-11-15 | Epic CDS Module | 92% alert override rate detected; 3 near-miss medication events traced to alert desensitization | Excessive low-value CDS alerts (1,200+/day per provider) due to overly broad rule configuration post-upgrade | 5 Whys + Fishbone | Closed | Dr. L. Thompson | 30
RCA-007 | Backup Failure for Cerner Database | Infrastructure | High | 2025-11-28 | Cerner Millennium DB | 14 consecutive backup failures undetected; RPO violation of 72+ hours discovered during DR drill | Backup agent license expired silently; monitoring alert routed to decommissioned email distribution list | 5 Whys + Fishbone | Closed | K. Nguyen | 8
RCA-008 | Telehealth Platform Latency Spike | Application | Medium | 2025-12-10 | Amwell Telehealth | Video consultations experiencing 5+ second latency; 40% patient dropout rate during peak hours | CDN provider capacity issue in US-East region compounded by unoptimized video transcoding settings | 5 Whys + Fishbone | Closed | P. Sharma | 12
RCA-009 | PHI Data Breach via Misconfigured SFTP | Security | Critical | 2025-12-22 | SFTP File Transfer Server | 1,247 patient records exposed on publicly accessible SFTP directory for 48 hours | Junior admin created SFTP directory with world-readable permissions; no automated compliance scan on file shares | 5 Whys + Fishbone | Closed | R. Johnson | 18
RCA-010 | Nurse Call System Integration Failure | Integration | Medium | 2026-01-08 | Hill-Rom Nurse Call + EHR | Nurse call events not flowing to EHR for 5 nursing units; manual documentation workaround required | TLS certificate expired on middleware server; auto-renewal job disabled during server migration 6 months prior | 5 Whys + Fishbone | Closed | J. Williams | 4
RCA-011 | Blood Bank Refrigerator Monitoring Alert Failure | IoT/Biomedical | Critical | 2026-01-15 | Tempus IC Monitoring | Temperature excursion in blood bank refrigerator undetected for 3 hours; 45 units of blood products quarantined | IoT gateway firmware update overwrote custom SNMP trap configuration; alerting threshold reverted to factory defaults | 5 Whys + Fishbone | In Progress | M. Chen
RCA-012 | Surgical Scheduling Double-Booking Defect | Application | High | 2026-01-22 | Epic OpTime | 17 OR double-bookings in one week; 4 surgical delays and 2 cancellations resulting in patient harm complaints | Race condition in concurrent booking API when two schedulers submit within 200ms window; locking mechanism insufficient | 5 Whys + Fishbone | In Progress | Dr. S. Patel
RCA-013 | Active Directory Sync Failure with HR System | Identity | Medium | 2026-01-30 | Azure AD Connect + Workday | New hires unable to access clinical systems for 48+ hours; 23 clinicians affected during onboarding week | Workday API schema change in January update broke AD Connect attribute mapping; no pre-prod validation of HR feed | 5 Whys + Fishbone | Closed | A. Rodriguez | 9
RCA-014 | Pharmacy Order Interface Duplicate Orders | Integration | High | 2026-02-03 | Epic-Omnicell Interface | Duplicate medication orders sent to pharmacy system; 8 near-miss dispensing events caught by pharmacist review | Message acknowledgment timeout set too low (2s); interface engine retransmitting before Omnicell could respond | 5 Whys + Fishbone | Open | K. Nguyen
RCA-015 | Disaster Recovery Failover Test Failure | Infrastructure | High | 2026-02-08 | DR Site — Azure East US 2 | Annual DR failover test failed; RTO exceeded target by 4 hours; clinical apps not accessible at DR site | DNS failover records stale; 6 clinical app endpoints still pointing to decommissioned primary IPs; runbook outdated | 5 Whys + Fishbone | Open | P. Sharma

## 5 Whys Analysis
RCA ID | Incident Title | Why #1 | Why #2 | Why #3 | Why #4 | Why #5 (Root Cause)
RCA-001 | EHR System Outage During Peak Hours | Why did the EHR go down? → Database connections were fully exhausted | Why were connections exhausted? → A new query from patch v12.3 was holding connections 10x longer than normal | Why was this query deployed? → It passed QA in a low-volume test environment that didn't simulate peak load | Why wasn't peak load simulated? → Performance testing environment lacks production-scale data (only 5% of prod volume) | ROOT CAUSE: No production-scale performance testing gate in the release pipeline; change management did not require load testing for database-impacting patches
RCA-002 | HL7 Interface Engine Message Backlog | Why did messages back up? → Interface engine processing threads were unresponsive | Why were threads unresponsive? → JVM heap memory was fully consumed, triggering constant GC cycles | Why was heap consumed? → HL7 parser module v6.2 introduced a memory leak in ADT message parsing | Why wasn't the leak caught? → Upgrade was tested for functional correctness only, no memory profiling performed | ROOT CAUSE: Vendor upgrade validation process lacks memory and performance profiling; no heap monitoring alerts configured for the interface engine JVM
RCA-003 | PACS Image Retrieval Failure | Why couldn't images be retrieved? → Storage I/O errors on the PACS archive LUNs | Why were there I/O errors? → SAN storage controller was intermittently dropping read requests | Why was the controller dropping requests? → Firmware bug in version 8.4.1 caused cache coherency failures under high read load | Why was this firmware version in production? → Vendor advisory was issued but categorized as 'low priority' by storage team | ROOT CAUSE: No automated vendor advisory triage process; firmware patching SLA not enforced for clinical-critical storage infrastructure
RCA-004 | Patient Portal Authentication Bypass | Why could authentication be bypassed? → Session tokens remained valid after password changes | Why weren't tokens invalidated? → OAuth2 callback handler did not check token issuance timestamp against last password change | Why was this check missing? → Original auth module was custom-built without following OWASP session management guidelines | Why weren't OWASP guidelines followed? → Security code review was not part of the SDLC for portal development | ROOT CAUSE: Absence of mandatory security code review in the software development lifecycle; no automated SAST/DAST scanning in CI/CD pipeline for patient-facing applications
RCA-005 | Medication Cabinet Network Failure | Why did the cabinets go offline? → Cabinets lost their IP addresses and couldn't reach the server | Why did they lose IPs? → DHCP scope for the biomedical VLAN was conflicting with the new switch configuration | Why was there a conflict? → Network engineer copied the switch config template without adjusting VLAN assignments for the biomedical subnet | Why wasn't this caught? → No pre-implementation network validation checklist exists for biomedical device VLANs | ROOT CAUSE: Change management process lacks a mandatory biomedical network impact assessment; no automated VLAN conflict detection in network change workflow
RCA-006 | Clinical Decision Support Alert Fatigue | Why are clinicians overriding 92% of alerts? → Most alerts are perceived as non-actionable or irrelevant to clinical context | Why are alerts irrelevant? → CDS rules were configured with overly broad trigger criteria after the Epic upgrade | Why were rules configured broadly? → Pharmacy committee applied conservative settings 'to be safe' without clinician workflow input | Why was there no clinician input? → CDS governance committee had not met in 8 months; no formal tuning process exists | ROOT CAUSE: Lack of ongoing CDS governance and alert tuning lifecycle; no feedback loop between clinician override data and rule optimization
RCA-007 | Backup Failure for Cerner Database | Why did backups fail for 14 days? → Backup agent reported license expiration and stopped all jobs | Why wasn't the failure detected? → Monitoring alert was configured to email a distribution list that was decommissioned | Why was the DL decommissioned? → IT reorganization 4 months prior moved the DBA team; DL migration was incomplete | Why was DL migration incomplete? → No centralized inventory of alert notification targets exists | ROOT CAUSE: No automated validation of monitoring alert delivery paths; alert notification audit not included in organizational change management procedures
RCA-008 | Telehealth Platform Latency Spike | Why was there 5+ second latency? → Video packets were being routed through a degraded CDN edge node | Why was the edge node degraded? → CDN provider had a capacity issue in US-East region during peak telehealth hours | Why did this affect us so severely? → Video transcoding was set to highest quality with no adaptive bitrate fallback | Why was there no adaptive bitrate? → Platform was deployed with default settings; optimization was deferred post-go-live | ROOT CAUSE: Telehealth platform deployed without performance optimization; no CDN failover or adaptive streaming configured; missing SLA monitoring for third-party service dependencies
RCA-009 | PHI Data Breach via Misconfigured SFTP | Why was PHI exposed? → SFTP directory containing patient files had world-readable (777) permissions | Why were permissions set incorrectly? → Junior admin created the directory manually without following the secure file share SOP | Why wasn't the SOP followed? → Admin was not trained on PHI data handling procedures; onboarding checklist was incomplete | Why was onboarding incomplete? → Security training module for file server administration was marked 'optional' | ROOT CAUSE: No automated compliance scanning for file share permissions; security training for PHI handling not mandatory for all infrastructure staff; missing preventive access control (default-deny)
RCA-010 | Nurse Call System Integration Failure | Why did nurse call events stop flowing? → Middleware server rejected all inbound connections from Hill-Rom system | Why did the server reject connections? → TLS certificate on the middleware had expired | Why did the certificate expire? → Auto-renewal job was disabled 6 months ago during server migration | Why wasn't this tracked? → Certificate inventory spreadsheet was not updated after migration; no automated cert monitoring | ROOT CAUSE: No centralized certificate lifecycle management tool; manual tracking of TLS certificates is error-prone and not audited during infrastructure changes
RCA-011 | Blood Bank Refrigerator Monitoring Alert Failure | Why was the temperature excursion undetected? → SNMP trap alerting was not firing for the blood bank sensors | Why weren't SNMP traps firing? → Custom trap configuration was overwritten during IoT gateway firmware update | Why was custom config overwritten? → Firmware update process did not include a config backup/restore step | Why was there no backup step? → Vendor's update utility resets to factory defaults by design; no pre-update SOP exists internally | ROOT CAUSE: No configuration backup procedure for IoT/biomedical device firmware updates; vendor firmware update behavior not documented or accounted for in change management
RCA-012 | Surgical Scheduling Double-Booking Defect | Why were ORs double-booked? → Two schedulers submitted bookings for the same slot within milliseconds | Why did the system allow this? → The booking API uses optimistic locking with insufficient conflict detection window | Why is the locking insufficient? → Original design assumed sequential access; concurrent API calls were not load-tested | Why wasn't concurrency tested? → Performance test cases focus on throughput, not on race condition scenarios | ROOT CAUSE: Application lacks pessimistic locking or serialized queue for critical resource booking; test strategy does not include concurrency/race condition test scenarios for scheduling APIs
RCA-013 | Active Directory Sync Failure with HR System | Why couldn't new hires access systems? → Their AD accounts were not provisioned automatically | Why weren't accounts provisioned? → AD Connect sync job was failing silently since the January Workday update | Why was it failing? → Workday changed API schema for employee attributes; AD Connect attribute mapping broke | Why wasn't this caught before production? → No pre-production validation environment mirrors the Workday-to-AD feed | ROOT CAUSE: No staging environment for HR-to-IAM integration testing; Workday API change notifications not monitored or included in change impact assessment
RCA-014 | Pharmacy Order Interface Duplicate Orders | Why were duplicate orders sent? → Interface engine retransmitted messages that were actually received by Omnicell | Why did retransmission occur? → ACK timeout was set to 2 seconds, but Omnicell processing takes 3-5 seconds under load | Why was the timeout set to 2 seconds? → Default value was used during initial interface configuration and never tuned | Why was it never tuned? → No post-go-live interface performance review process exists; SLA for message acknowledgment undefined | ROOT CAUSE: Interface engine timeout not tuned to receiving system performance characteristics; no post-implementation performance baseline or ongoing SLA monitoring for clinical interfaces
RCA-015 | Disaster Recovery Failover Test Failure | Why did DR failover fail? → Clinical applications could not resolve to DR site endpoints | Why couldn't they resolve? → DNS failover records were pointing to decommissioned primary datacenter IPs | Why were DNS records stale? → DR runbook was last updated 18 months ago; decommissioned IPs never removed | Why wasn't the runbook updated? → No mandatory DR runbook review cycle tied to infrastructure changes | ROOT CAUSE: DR runbooks not maintained as living documents; no automated DNS failover validation; infrastructure decommissioning process does not include DR documentation update step

## Fishbone Analysis
RCA ID | Incident Title | People | Process | Technology | Environment | Materials/Data | Management
RCA-001 | EHR System Outage | DBA team understaffed; no on-call coverage during patch window | No performance testing gate in change management; post-deployment validation skipped | Query optimizer not tested against production data volumes; connection pool limits too low | Peak census day (Monday AM); higher than average concurrent users | Test data only 5% of production size; synthetic data lacks complexity | No executive sponsor for performance testing program; budget for load testing tools declined
RCA-002 | HL7 Interface Backlog | Integration engineer on PTO during upgrade; backup resource unfamiliar with Rhapsody | Vendor upgrade process lacks memory profiling step; no rollback trigger defined | JVM heap monitoring not configured; HL7 parser v6.2 memory leak | High ADT volume during flu season increased message throughput 3x | HL7 v2.5.1 ADT messages with large Z-segments consuming excess memory | Interface engine maintenance window too short for thorough validation
RCA-003 | PACS Image Retrieval Failure | Storage team classified vendor advisory as low priority without clinical input | No firmware patching SLA for clinical storage; vendor advisory triage not automated | SAN controller firmware bug in v8.4.1; cache coherency failure under load | End-of-quarter radiology volume surge increased I/O demands on PACS storage | Large DICOM studies (CT/MRI) amplified the I/O issue; archive LUNs near capacity | Storage infrastructure not classified as clinical-critical in asset management
RCA-004 | Patient Portal Auth Bypass | Developer lacked OWASP training; no security champion assigned to portal team | SDLC missing mandatory security code review; no SAST/DAST in CI/CD pipeline | Custom OAuth2 handler; session tokens not tied to password change events | Increased portal usage during open enrollment amplified exposure window | OWASP session management guidelines not in developer knowledge base | Security team not consulted during portal architecture design; no AppSec budget
RCA-005 | Medication Cabinet Network Failure | Network engineer unfamiliar with biomedical VLAN requirements; no peer review | No biomedical impact assessment in network change management process | VLAN conflict detection not automated; DHCP scope overlaps possible | Switch replacement scheduled during shift change; biomedical team not available to verify | Network config template missing biomedical subnet parameters | Biomedical and network teams operate in silos; no joint change review board
RCA-006 | CDS Alert Fatigue | Clinicians not consulted during CDS rule configuration; pharmacy-only decision | No CDS governance lifecycle; alert tuning not scheduled; override data not reviewed | Epic CDS engine lacks context-aware filtering; binary alert logic only | Post-upgrade alert volume increased 4x; coincided with new resident onboarding | Clinical evidence for alert thresholds outdated (2019 guidelines) | CDS governance committee inactive for 8 months; no executive accountability for alert optimization
RCA-007 | Backup Failure — Cerner DB | DBA team restructured; responsibilities unclear; no clear backup owner | No monitoring alert delivery validation; decommissioned DL not caught in reorg | Backup agent license expiration not monitored; silent failure mode | IT reorganization created gaps in operational responsibilities | License renewal calendar not maintained; vendor renewal notices sent to wrong contact | Organizational change management did not include operational handoff checklist
RCA-008 | Telehealth Latency Spike | Telehealth team lacked CDN/video optimization expertise during deployment | No post-go-live performance optimization sprint; SLA monitoring not configured | Default video transcoding settings; no adaptive bitrate; single CDN region | US-East CDN capacity degraded during peak telehealth hours (11AM-2PM EST) | Vendor documentation on adaptive streaming not reviewed during implementation | Telehealth launch prioritized speed-to-market over performance engineering
RCA-009 | PHI Breach via SFTP | Junior admin not trained on PHI handling; security training marked optional | Secure file share SOP not enforced; no automated permission compliance scan | No default-deny ACL on file shares; manual permission assignment | End-of-year data exchange deadline created pressure to set up SFTP quickly | PHI data classification labels not applied to files; no DLP scanning on SFTP | Security onboarding training not mandatory for infrastructure staff; audit gap
RCA-010 | Nurse Call Integration Failure | Middleware admin unaware cert auto-renewal was disabled during migration | No certificate lifecycle management process; manual spreadsheet tracking | TLS cert expired; auto-renewal disabled 6 months ago; no cert monitoring tool | Server migration project 6 months prior created tech debt not tracked | Certificate inventory not updated post-migration; no source of truth | Infrastructure migration project closeout did not verify all operational dependencies
RCA-011 | Blood Bank Monitor Alert Failure | Biomedical engineer did not verify alerting post-firmware update | No config backup/restore step in firmware update SOP; no post-update checklist | IoT gateway firmware resets to factory defaults; custom SNMP traps lost | Blood bank refrigerator in older wing with limited IoT infrastructure redundancy | Vendor documentation does not warn about config reset during update | IoT device management not integrated into enterprise change management
RCA-012 | Surgical Double-Booking Defect | Schedulers making rapid concurrent bookings during block release windows | Concurrency/race condition testing not in QA test strategy | Optimistic locking insufficient; no serialized queue for OR booking API | Block time release at 7AM triggers simultaneous scheduling activity | Test data does not simulate concurrent API call patterns | Application architecture review did not assess concurrent access scenarios for critical resources
RCA-013 | AD Sync Failure with Workday | Identity team not subscribed to Workday API change notifications | No staging environment for HR-to-IAM integration; no pre-prod validation | AD Connect attribute mapping hardcoded; not resilient to schema changes | January Workday update coincided with large onboarding cohort | Workday API changelog not reviewed before production sync cycle | Vendor API change management not included in internal change impact assessment
RCA-014 | Pharmacy Duplicate Orders | Interface analyst used default timeout without consulting Omnicell performance specs | No post-go-live interface performance baseline; ACK SLA undefined | 2-second ACK timeout too low; Omnicell needs 3-5 seconds under peak load | Pharmacy order volume peaks during morning med pass (6-8AM); timeout most likely to hit | Omnicell system performance documentation not referenced during interface design | No interface performance review cadence; clinical interface SLAs not established
RCA-015 | DR Failover Test Failure | DR coordinator role vacant for 3 months; no interim coverage assigned | DR runbook not updated with infrastructure changes; no mandatory review cycle | DNS failover records stale; pointing to decommissioned IPs; no automated validation | Primary datacenter decommissioned 6 months ago; DR was not retested post-decom | Runbook documentation outdated (18 months); IP address inventory not current | Decommissioning process does not mandate DR documentation updates; no DR governance board

## Preventive Actions
Action ID | RCA ID | Preventive Action | Action Type | Priority | Owner | Target Date | Status | Verification Method | Notes
PA-001 | RCA-001 | Implement mandatory load testing gate in CI/CD pipeline for all database-impacting changes | Preventive | Critical | DevOps Lead | 2025-10-15 | Closed | Verify load test results attached to every DB change request | Integrated with Jenkins pipeline
PA-002 | RCA-001 | Scale performance test environment to 50% of production data volume | Preventive | High | Infra Manager | 2025-11-30 | Closed | Compare test env metrics to production baseline | Budget approved Q4 2025
PA-003 | RCA-001 | Configure database connection pool monitoring with auto-scaling alerts | Detective | High | DBA Team | 2025-10-01 | Closed | Alert fires when pool reaches 80% utilization | Integrated with PagerDuty
PA-004 | RCA-002 | Add JVM heap memory monitoring and alerting for all interface engine instances | Detective | High | Integration Team | 2025-10-15 | Closed | Heap usage alerts at 70% and 85% thresholds | Grafana dashboard created
PA-005 | RCA-002 | Include memory profiling in vendor upgrade validation checklist | Preventive | Medium | Integration Lead | 2025-11-01 | Closed | Memory profiling report required before upgrade approval | Added to change management template
PA-006 | RCA-003 | Automate vendor security advisory ingestion and triage for clinical infrastructure | Preventive | Critical | Security Ops | 2025-11-15 | Closed | Weekly automated advisory report with severity classification | ServiceNow integration complete
PA-007 | RCA-003 | Define firmware patching SLA: Critical=72hrs, High=2wks for clinical storage | Preventive | High | Infra Manager | 2025-10-30 | Closed | Monthly compliance report against firmware SLA | Policy document signed by CIO
PA-008 | RCA-004 | Implement mandatory SAST/DAST scanning in CI/CD for all patient-facing applications | Preventive | Critical | AppSec Lead | 2025-11-15 | Closed | Zero critical findings before production deployment | SonarQube + OWASP ZAP integrated
PA-009 | RCA-004 | Mandate OWASP session management training for all development teams annually | Preventive | High | Training Manager | 2025-12-01 | Closed | Training completion tracked in LMS; 100% compliance required | Added to annual security training
PA-010 | RCA-005 | Create automated VLAN conflict detection for all network changes affecting biomedical subnets | Preventive | High | Network Lead | 2025-12-15 | Closed | Pre-change automated validation report generated | Ansible playbook deployed
PA-011 | RCA-005 | Establish joint biomedical-network change review board (monthly) | Preventive | Medium | IT Director | 2025-12-01 | Closed | Meeting minutes and change review log maintained | First meeting held Nov 2025
PA-012 | RCA-006 | Reactivate CDS governance committee with quarterly alert tuning reviews | Preventive | High | CMIO | 2025-12-15 | Closed | Quarterly override rate report published; target <70% override rate | Committee charter renewed
PA-013 | RCA-006 | Implement clinician feedback loop for CDS alert relevance scoring | Preventive | Medium | Clinical Informatics | 2026-01-31 | Closed | Monthly alert relevance survey with >50% response rate | Integrated into Epic InBasket
PA-014 | RCA-007 | Deploy automated alert delivery validation (test alert monthly to all notification targets) | Detective | High | Monitoring Team | 2025-12-15 | Closed | Monthly test alert delivery confirmation from all recipients | Automated with ServiceNow workflow
PA-015 | RCA-007 | Create centralized notification target inventory with quarterly audit | Preventive | Medium | IT Ops Manager | 2026-01-15 | Closed | Quarterly audit report with DL membership verification | CMDB integration complete
PA-016 | RCA-008 | Configure multi-region CDN failover and adaptive bitrate streaming for telehealth | Corrective | High | Telehealth Lead | 2026-01-15 | Closed | Failover test passes; latency <500ms during CDN regional outage | US-East and US-West CDN configured
PA-017 | RCA-008 | Implement third-party SLA monitoring dashboard for all critical vendor services | Detective | Medium | Vendor Mgmt | 2026-02-01 | Closed | Real-time SLA dashboard with automated breach alerts | Datadog integration live
PA-018 | RCA-009 | Deploy automated file share permission compliance scanning (daily) | Detective | Critical | Security Ops | 2026-01-10 | Closed | Daily scan report; auto-remediation for world-readable PHI directories | CrowdStrike Falcon integrated
PA-019 | RCA-009 | Make PHI data handling training mandatory for all infrastructure staff during onboarding | Preventive | Critical | CISO | 2026-01-15 | Closed | 100% completion within 30 days of hire; annual refresher required | LMS enrollment automated via HR feed
PA-020 | RCA-010 | Implement centralized certificate lifecycle management (CLM) tool | Preventive | High | Infra Manager | 2026-02-28 | In Progress | All certificates tracked; auto-renewal enabled; 30-day expiry alerts | Evaluating Venafi vs AppViewX
PA-021 | RCA-010 | Add certificate verification to infrastructure migration closeout checklist | Preventive | Medium | Project Mgmt | 2026-01-30 | Closed | Migration signoff requires certificate inventory reconciliation | Template updated in ServiceNow
PA-022 | RCA-011 | Create mandatory config backup/restore SOP for all IoT/biomedical firmware updates | Preventive | Critical | Biomedical Eng | 2026-02-15 | In Progress | Config backup verified pre-update; restore validated post-update | Draft SOP under clinical engineering review
PA-023 | RCA-011 | Integrate IoT device management into enterprise change management workflow | Preventive | High | IT Director | 2026-03-01 | Open | All IoT firmware changes require change ticket with config backup evidence | Scope being defined with clinical engineering
PA-024 | RCA-012 | Implement pessimistic locking or serialized queue for OR scheduling API | Corrective | Critical | Epic Dev Team | 2026-02-28 | In Progress | Zero double-bookings in 30-day post-fix monitoring period | Epic enhancement request submitted
PA-025 | RCA-012 | Add concurrency and race condition test scenarios to QA test strategy | Preventive | High | QA Lead | 2026-02-15 | In Progress | Concurrency test suite runs in every sprint; 100% pass required | JMeter concurrent user scripts in development
PA-026 | RCA-013 | Build staging environment mirroring Workday-to-AD integration for pre-prod validation | Preventive | High | Identity Team | 2026-03-01 | Open | All Workday API changes validated in staging before production sync | Azure sandbox environment requested
PA-027 | RCA-013 | Subscribe to Workday API changelog and integrate into change impact assessment | Preventive | Medium | Vendor Mgmt | 2026-02-15 | In Progress | API change notifications reviewed weekly by identity team | RSS feed configured
PA-028 | RCA-014 | Tune interface ACK timeout to match Omnicell performance profile (5s baseline + buffer) | Corrective | High | Interface Team | 2026-02-20 | In Progress | Zero duplicate orders in 14-day post-change monitoring | Testing 7-second timeout in pre-prod
PA-029 | RCA-014 | Establish quarterly interface performance review cadence with defined SLAs | Preventive | Medium | Integration Lead | 2026-03-15 | Open | Quarterly SLA compliance report for all clinical interfaces | Template being developed
PA-030 | RCA-015 | Mandate DR runbook review within 30 days of any infrastructure change | Preventive | Critical | DR Coordinator | 2026-03-01 | Open | Infrastructure change ticket requires DR documentation update evidence | Policy draft under review
PA-031 | RCA-015 | Implement automated DNS failover validation (monthly synthetic tests) | Detective | High | Network Team | 2026-03-15 | Open | Monthly automated DNS resolution test from DR site with pass/fail report | Evaluating Catchpoint vs ThousandEyes
PA-032 | RCA-015 | Include DR documentation update in infrastructure decommissioning checklist | Preventive | High | IT Ops Manager | 2026-02-28 | Open | Decommissioning signoff requires DR runbook reconciliation | ServiceNow workflow update pending

## RCA Template
ROOT CAUSE ANALYSIS (RCA) TEMPLATE
Healthcare IT Problem Management
1. INCIDENT DETAILS
RCA ID:
Incident Title:
Date Identified:
Severity: | Critical / High / Medium / Low
Affected System:
Category: | Application / Infrastructure / Network / Security / Integration / IoT
Incident Owner:
RCA Lead:
Impact Description:
2. FIVE WHYS ANALYSIS
Problem Statement:
Why #1:
Why #2:
Why #3:
Why #4:
Why #5 (Root Cause):
3. FISHBONE (ISHIKAWA) ANALYSIS
People:
Process:
Technology:
Environment:
Materials / Data:
Management:
4. PREVENTIVE / CORRECTIVE ACTIONS
Action # | Description | Owner / Target Date
Action 1
Action 2
Action 3
Action 4
Action 5
5. REVIEW & SIGN-OFF
RCA Lead Signature:
Problem Manager:
IT Director / CISO:
Review Date:
Next Review Date:

## Summary Statistics
RCA LIBRARY — SUMMARY STATISTICS
RCAs by Severity
Severity | Count | % of Total
Critical | 4 | 26.67%
High | 5 | 33.33%
Medium | 4 | 26.67%
Low | 2 | 13.33%
RCAs by Category
Category | Count | % of Total
Application | 3 | 21.43%
Infrastructure | 3 | 21.43%
Integration | 3 | 21.43%
Security | 2 | 14.29%
Network | 1 | 7.143%
Identity | 1 | 7.143%
IoT/Biomedical | 1 | 7.143%
Preventive Actions by Status
Status | Count | % of Total
Closed | 19 | 59.38%
In Progress | 6 | 18.75%
Open | 7 | 21.88%
Key Metrics
Total RCAs in Library | 15
Total Preventive Actions | 32
Avg Days to Resolve (Closed RCAs) | 12.3
RCAs with All Actions Closed | 9
RCAs with Open Actions | 6
Action Closure Rate | 59.4%